## Sheet1
SL_No | KPI | Details | Recipient | Data Frequency | Discussion/Action Point
1 | GA | Tgt vs Ach, MTD vs LMTD, DRR/CRR/RR | ZM, DD, Top | D-1 | Sales team will share the logic of DRR, CRR, RR. Responsible : Mairaj Bhai/Tareq Bhai.
2 | GA | today, yesterday, last week same day | ZM, DD, Top | Near Real time | BI will shared the Source table with DWH . Responsible :Nahid Bhai 11-Jan-2023 : Nahid Bhai(BI) already shared the query with DWH in 10-Jan-2023
DWH will check the ETL time from Getting Table information. Responsible : Tanvir Bhai
3 | GA | BP wise today, MTD, Target vs Ach, GA QTY , Retail Count | ZM, DD, Top | Near Real time | GA QTY Column is not require. Source as KPI(SL-2).
Table Format :BP MSISDN, Retailer Code, Date, GA Count
Nahid Bhai will check the BI Dump again and confirm to the forum. 11-Jan-2023 : Nahid Bhai(BI) already shared the query with DWH in 10-Jan-2023
*BP Target will be uploaded through RSO App.
4 | GA | RSO wise today, MTD, GA QTY , Retail Count | RSO, ZM | Near Real time | Source same as KPI(SL-2).
5 | All Bundle | Tgt vs Ach, MTD vs LMTD, DRR/CRR/RR | ZM, DD, Top | D-1 | Sales team will share the logic of DRR, CRR, RR. Responsible : Mairaj Bhai/Tareq Bhai.
6 | All Bundle | today, yesterday, last week same day | ZM, DD, Top | Near Real time
Table Format : Retailer Code/ITOPUP MSISDN, Deno, Count, Deno Type
Deno wise hit Count. DWH will sync with Minhaz. Responsible : Tanvir Bhai.
7 | All Bundle | RSO wise tgt vs ach, MTD vs LMTD | RSO, ZM | D-1
8 | Data | Tgt vs Ach, DRR/CRR/RR | ZM, DD, Top | D-1 | Sales team will share the logic of DRR, CRR, RR. Responsibe : Mairaj Bhai/Tareq Bhai.
9 | Data | MTD vs LMTD | ZM, DD, Top | D-1
10 | Data | today, yesterday, last week same day | ZM, DD, Top | Near Real time | Source Same as SL (SL-6)
11 | Data | RSO wise tgt vs ach, MTD vs LMTD | RSO, ZM | D-1
12 | EV Secondary | MTD vs LMTD, today, yesterday, last week same day | RSO, ZM, DD, Top | Near Real time | DWH will check the feasibility. Responsible : Tanvir Bhai
13 | EV Tertiary | Tgt vs Ach, MTD vs LMTD, today, yesterday, last week same day | RSO, ZM, DD, Top | Near Real time | DWH will check the feasibility. Responsible : Tanvir Bhai
14 | SC Secondary | Tgt vs Ach, MTD vs LMTD | RSO, ZM, DD, Top | D-1 | Target will be uploaded from App End(Need to develop Capability)
15 | SC Tertiary | Tgt vs Ach, MTD vs LMTD | ZM, DD, Top | D-1 | Target will be uploaded from App End(Need to develop Capability)
16 | LSO | MTD vs LMTD | RSO, ZM, DD, Top | D-1
- Required to develop new logic from BI end. Responsible : Nahid Bhai
Table Format : RSO Code, Count
- Sales will share the details logic definition. Responsible : Tareq Bhai
17 | DLSO | MTD vs LMTD | RSO, ZM, DD, Top | D-1 | Nahid Bhai will check the feasibility to develop this KPI.
Table Format : RSO Code, Count
- Sales will share the details logic definition. Responsible : Tareq Bhai
18 | SSO | MTD vs LMTD | RSO, ZM, DD, Top | D-1 | BI Team will check the feasibility to develop this KPI. Responsible : Nahid Bhai
RSO Code, Retailer Count
- Sales will share the details logic definition. Responsible : Tareq Bhai
19 | DSSO | MTD vs LMTD | RSO, ZM, DD, Top | D-1 | Nahid Bhai will check the feasibility to develop this KPI.
Table Format : RSO Code, Retailer Count
- Sales will share the details logic definition. Responsible : Tareq Bhai
20 | DSO | Tgt vs Ach, MTD vs LMTD | ZM, DD, Top | D-1 | This item will discuss on next session.
21 | BSO | Tgt vs Ach, MTD vs LMTD | ZM, DD, Top | D-1 | This item will discuss on next session.
22 | Retail SCR | Less than 2 days stock %, Less than 1 day stock % | RSO, ZM, DD, Top |  | BI Team will share the logic with DWH Team. Responsible : Nahid Bhai
Table Format : 2 Day less Stock, Retailer Count
Table Format : 1 Day less Stock, Retailer Count
- Sales Team will confirm the Data Frequency. Responsible : Tareq Bhai
23 | Retail SCR | last X days low balance | RSO, ZM, DD, Top |  | Sales Team will confirm the data Frequency and X days logic.
Also, check whether KPI 22 & 23 is same or not. After then, confirm the forum. Responsible : Tareq Bhai.
24 | M1/M2 Decay | BP GA Decay , Distributor Decay | ZM, DD, Top |  | Logic require to development from BI end. Then share the logic with DWH.
Responsible: Nahid Bhai
Table Format : BP MSISDN ,Retailer Code, M1 Count, M2 Count
Sales team will confirm the data frequency . Responsible : Tareq Bhai.
25 | Retail App Utilization |  | ZM, DD, Top |  | outlet, utilization %, trans % Total C2S count will consider from regular/Daily EV Dump For Retailer Hit count Need to Sit with Retailer App Team or Explore in C2S Big Data Team Dump
Responsible : Maruf & Mairaj Bhai
26 | RSO App Utilization |  | ZM, DD, Top | Near real time | Data Available at RSO App End.
27 | RSO App Utilization |  | ZM, DD, Top | D-1 | Data Available at RSO App End.
28 | Deno | today, yesterday, last week same day, MTD Vs LMTD, 3D, 7D, 30D | ZM, DD, Top |  | BI Team will share logic with DWH for below Table format. Responsible : Nahid Bhai Table Format : Retailer Code, Deno , Hit Count -Sales team will share the details logic with the Forum. Responsible :Mairaj Bhai. Required to develop capability enter option for 3D, 7D, 30D 3D, 7D, 30D(Today Data Near Real Time) - Hit Count
29 | Site | GA, Subbase, Rev, LSO, SSO (MTD, LMTD) | ZM, DD, Top |  | This item will discuss on next session.
30 | LUS, SRAN, Rest | Site, GA, Subbase, Rev, LSO, SSO (MTD, LMTD) |  |  | This item will discuss on next session.