## Sheet1
SL_No | KPI | Details | Recipient | Data Frequency | Discussion/Action Point | Logic Feedback | Data Availability DWH(Y/N)
1 | GA | Tgt vs Ach, MTD vs LMTD, DRR/CRR/RR | ZM, DD, Top | D-1 | Sales team will share the logic of DRR, CRR, RR. Responsible : Mairaj Bhai/Tareq Bhai. | DRR (Daily Run Rate) : Target / Month Days CRR (Current Run Rate): Achievement / days elapsed RRR (Required Run Rate): (Target - Achievement)/remaing days | N
2 | GA | today, yesterday, last week same day | ZM, DD, Top | Near Real time | BI will shared the Source table with DWH . Responsible :Nahid Bhai 11-Jan-2023 : Nahid Bhai(BI) already shared the query with DWH in 10-Jan-2023 |  | Y
DWH will check the ETL time from Getting Table information. Responsible : Tanvir Bhai
3 | GA | BP wise today, MTD, Target vs Ach, GA QTY , Retail Count | ZM, DD, Top | Near Real time | GA QTY Column is not require. Source as KPI(SL-2).
Table Format :BP MSISDN, Retailer Code, Date, GA Count
[5 empty] | Nahid Bhai will check the BI Dump again and confirm to the forum. 11-Jan-2023 : Nahid Bhai(BI) already shared the query with DWH in 10-Jan-2023 |  | Y
*BP Target will be uploaded through RSO App.
4 | GA | RSO wise today, MTD, GA QTY , Retail Count | RSO, ZM | Near Real time | Source same as KPI(SL-2). 11-Jan-2023 : Nahid Bhai(BI) already shared the query with DWH in 10-Jan-2023 |  | Y
5 | All Bundle | Tgt vs Ach, MTD vs LMTD, DRR/CRR/RR | ZM, DD, Top | D-1 | Sales team will share the logic of DRR, CRR, RR. Responsible : Mairaj Bhai/Tareq Bhai. | DRR (Daily Run Rate) : Target / Month Days CRR (Current Run Rate): Achievement / days elapsed RRR (Required Run Rate): (Target - Achievement)/remaing days | N
6 | All Bundle | today, yesterday, last week same day | ZM, DD, Top | Near Real time
[5 empty] | Table Format : Retailer Code/ITOPUP MSISDN, Deno, Count, Deno Type |  | DWH will check the fesibility
Deno wise hit Count. DWH will sync with Minhaz. Responsible : Tanvir Bhai.
7 | All Bundle | RSO wise tgt vs ach, MTD vs LMTD | RSO, ZM | D-1
8 | Data | Tgt vs Ach, DRR/CRR/RR | ZM, DD, Top | D-1 | Sales team will share the logic of DRR, CRR, RR. Responsibe : Mairaj Bhai/Tareq Bhai. | DRR (Daily Run Rate) : Target / Month Days CRR (Current Run Rate): Achievement / days elapsed RRR (Required Run Rate): (Target - Achievement)/remaing days | N
9 | Data | MTD vs LMTD | ZM, DD, Top | D-1 |  |  | N
10 | Data | today, yesterday, last week same day | ZM, DD, Top | Near Real time | Source Same as SL (SL-6) |  | DWH will check the fesibility
11 | Data | RSO wise tgt vs ach, MTD vs LMTD | RSO, ZM | D-1 |  |  | N
12 | EV Secondary | MTD vs LMTD, today, yesterday, last week same day | RSO, ZM, DD, Top | Near Real time | DWH will check the feasibility. Responsible : Tanvir Bhai |  | DWH will check the fesibility
13 | EV Tertiary | Tgt vs Ach, MTD vs LMTD, today, yesterday, last week same day | RSO, ZM, DD, Top | Near Real time | DWH will check the feasibility. Responsible : Tanvir Bhai |  | DWH will check the fesibility
14 | SC Secondary | Tgt vs Ach, MTD vs LMTD | RSO, ZM, DD, Top | D-1 | Target will be uploaded from App End(Need to develop Capability) |  | N
15 | SC Tertiary | Tgt vs Ach, MTD vs LMTD | ZM, DD, Top | D-1 | Target will be uploaded from App End(Need to develop Capability) |  | N
16 | LSO | MTD vs LMTD | RSO, ZM, DD, Top | D-1
- Required to develop new logic from BI end. Responsible : Nahid Bhai
Table Format : RSO Code, Count
[5 empty] | - Sales will share the details logic definition. Responsible : Tareq Bhai | LSO (Load Selling Outlet): Active itopup Selling retailer with minimum 100 Tk. C2S and minimum 4 days transaction in a month | Y
17 | DLSO | MTD vs LMTD | RSO, ZM, DD, Top | D-1 | Nahid Bhai will check the feasibility to develop this KPI.
[5 empty] | Table Format : RSO Code, Count |  | Y
[5 empty] | - Sales will share the details logic definition. Responsible : Tareq Bhai | DLSO(Daily Load Selling Outlet): Active itopup Selling retailer with minimum 1 transaction each day of current month
18 | SSO | MTD vs LMTD | RSO, ZM, DD, Top | D-1 | BI Team will check the feasibility to develop this KPI. Responsible : Nahid Bhai
[5 empty] | RSO Code, Retailer Count |  | Y
[5 empty] | - Sales will share the details logic definition. Responsible : Tareq Bhai | SSO (SIM Selling Outlet): Active SIM Selling retailer with minimum 2 GA in a month
19 | DSSO | MTD vs LMTD | RSO, ZM, DD, Top | D-1 | Nahid Bhai will check the feasibility to develop this KPI.
[5 empty] | Table Format : RSO Code, Retailer Count |  | Y
[5 empty] | - Sales will share the details logic definition. Responsible : Tareq Bhai | DSSO (Daily SIM Selling Outlet): Active SIM Selling retailer with minimum 1 GA each day of current month
20 | DSO | Tgt vs Ach, MTD vs LMTD | ZM, DD, Top | D-1 | This item will discuss on next session. | DSO (Data Selling Outlet): Active itopup Selling retailer with minimum 200 Tk. Mixed Bundle or Data Bundle sales and minimum 3 days transaction in a month | N
21 | BSO | Tgt vs Ach, MTD vs LMTD | ZM, DD, Top | D-1 | This item will discuss on next session. | BSO (Bundle Selling Outlet): Active itopup Selling retailer with minimum 200 Tk. Mixed Bundle or Data Bundle or Voice Bundle sales and minimum 4 days transaction in a month | N
22 | Retail SCR | Less than 2 days stock %, Less than 1 day stock % | RSO, ZM, DD, Top |  | BI Team will share the logic with DWH Team. Responsible : Nahid Bhai
[5 empty] | Table Format : 2 Day less Stock, Retailer Count |  | y
Table Format : 1 Day less Stock, Retailer Count
[5 empty] | - Sales Team will confirm the Data Frequency. Responsible : Tareq Bhai | Stock Definition: Total C2S amount/Number of transacted day count= 1 day SCR for a particular month
23 | Retail SCR | last X days low balance | RSO, ZM, DD, Top |  | Sales Team will confirm the data Frequency and X days logic.
[5 empty] | Also, check whether KPI 22 & 23 is same or not. After then, confirm the forum. Responsible : Tareq Bhai. | Low Balance definition: Less than 200/300/500 Tk balance in a particular day. (will be decided soon) | Y
24 | M1/M2 Decay | BP GA Decay , Distributor Decay | ZM, DD, Top |  | Logic require to development from BI end. Then share the logic with DWH.
[5 empty] | Responsible: Nahid Bhai |  | Y
Table Format : BP MSISDN ,Retailer Code, M1 Count, M2 Count
[5 empty] | Sales team will confirm the data frequency . Responsible : Tareq Bhai. | Monthly
25 | Retail App Utilization |  | ZM, DD, Top |  | outlet, utilization %, trans % Total C2S count will consider from regular/Daily EV Dump For Retailer Hit count Need to Sit with Retailer App Team or Explore in C2S Big Data Team Dump |  | Need to check with retailer app
Responsible : Maruf & Mairaj Bhai
26 | RSO App Utilization |  | ZM, DD, Top | Near real time | Data Available at RSO App End. |  | Ok
27 | RSO App Utilization |  | ZM, DD, Top | D-1 | Data Available at RSO App End. |  | OK
28 | Deno | today, yesterday, last week same day, MTD Vs LMTD, 3D, 7D, 30D | ZM, DD, Top |  | BI Team will share logic with DWH for below Table format. Responsible : Nahid Bhai Table Format : Retailer Code, Deno , Hit Count -Sales team will share the details logic with the Forum. Responsible :Mairaj Bhai. Required to develop capability enter option for 3D, 7D, 30D 3D, 7D, 30D(Today Data Near Real Time) - Hit Count | Deno list will be maintained with flag 3D, 7D, 30D, Active flag, date flag | Y
29 | Site | GA, Subbase, Rev, LSO, SSO (MTD, LMTD) | ZM, DD, Top | D-1 | As per Sales team this data is available at DMS end. We need to check with DMS team along with Sales team. Responsible: Maruf/Mairaj Bhai |  | Need to check with DMS
30 | LUS, SRAN, Rest | Site, GA, Subbase, Rev, LSO, SSO (MTD, LMTD) |  | D-1 | Sales team will share the details logic of Low Utilization Site(LUS) & rest Site. Reponsible : Mairaj Bhai. BI Team will explore whether this logic available at their end or not. Responsible : Nahid Bhai | LUS Low Utilization Site: this logic is available with Jayanta BI REST: Total Macro Site - SRAN - LUS - Restricted site SRAN: SRAN flag exists in DMS

## Priority 1
SL_No | KPI | Details | Recipient | Data Frequency | Discussion/Action Point | Logic Feedback | Data Availability DWH(Y/N)
1 | GA | Tgt vs Ach, MTD vs LMTD, DRR/CRR/RR | ZM, DD, Top | D-1 | Sales team will share the logic of DRR, CRR, RR. Responsible : Mairaj Bhai/Tareq Bhai. | DRR (Daily Run Rate) : Target / Month Days CRR (Current Run Rate): Achievement / days elapsed RRR (Required Run Rate): (Target - Achievement)/remaing days | N
5 | All Bundle | Tgt vs Ach, MTD vs LMTD, DRR/CRR/RR | ZM, DD, Top | D-1 | Sales team will share the logic of DRR, CRR, RR. Responsible : Mairaj Bhai/Tareq Bhai. | DRR (Daily Run Rate) : Target / Month Days CRR (Current Run Rate): Achievement / days elapsed RRR (Required Run Rate): (Target - Achievement)/remaing days | N
8 | Data | Tgt vs Ach, DRR/CRR/RR | ZM, DD, Top | D-1 | Sales team will share the logic of DRR, CRR, RR. Responsibe : Mairaj Bhai/Tareq Bhai. | DRR (Daily Run Rate) : Target / Month Days CRR (Current Run Rate): Achievement / days elapsed RRR (Required Run Rate): (Target - Achievement)/remaing days | N
9 | Data | MTD vs LMTD | ZM, DD, Top | D-1 |  |  | N
20 | DSO | Tgt vs Ach, MTD vs LMTD | ZM, DD, Top | D-1 | This item will discuss on next session. | DSO (Data Selling Outlet): Active itopup Selling retailer with minimum 200 Tk. Mixed Bundle or Data Bundle sales and minimum 3 days transaction in a month | N
21 | BSO | Tgt vs Ach, MTD vs LMTD | ZM, DD, Top | D-1 | This item will discuss on next session. | BSO (Bundle Selling Outlet): Active itopup Selling retailer with minimum 200 Tk. Mixed Bundle or Data Bundle or Voice Bundle sales and minimum 4 days transaction in a month | N
26 | RSO App Utilization |  | ZM, DD, Top | Near real time | Data Available at RSO App End. |  | Ok
27 | RSO App Utilization |  | ZM, DD, Top | D-1 | Data Available at RSO App End. |  | OK
7 | All Bundle | RSO wise tgt vs ach, MTD vs LMTD | RSO, ZM | D-1