## Test Cases on KPI Reports
|  | Project Name: Digital Sales Eco-System_Core KPI Reporting | Reviewed By :
|  | Test Start Date: | Prepared By: MD Nahid Hassan
|  | Test End Date: | UAT Feedback:
|  | Developer: | Comments:
Test ID. | Feature/Page | Test Cases | Expected Output | Test Data | Actual Output | Pass/Fail | UAT Feedback | Tested By | Date
BIR01 | FR-1, KPI: GA | Verify that a new Report feature and page of KPI “GA” is available and browsable appropriately. | Users can view that a new Report feature and page of KPI “GA” is available, browsable, and working appropriately.
BIR02 | FR-1, KPI: GA | Verify that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately. | Users can view that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately.
BIR03 | FR-1, KPI: GA | Verify that User wise summarized data view after login is available and working appropriately. | Users can view that User type-wise summarized data view after login is available and working appropriately.
BIR04 | FR-1, KPI: GA | Verify that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page. | Users can see that to view summarized data for Top (Cluster Director, Director) level users, Users must view all “Clusters” summarized data on the default page.
BIR05 | FR-1, KPI: GA | Verify that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”. | Users can view that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”.
BIR06 | FR-1, KPI: GA | Verify that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show. | Users can view that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show.
BIR07 | FR-1, KPI: GA | Verify that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”. | Users can see that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”.
BIR08 | FR-1, KPI: GA | Verify that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”. | Users can view that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”.
BIR09 | FR-1, KPI: GA | Verify that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”. | Users can view that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”.
BIR10 | FR-1, KPI: GA | Verify that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”. | Users can view that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”.
BIR11 | FR-1, KPI: GA | Verify that the data view Logic for DRR (Daily Run Rate) is "Target / Month Days" and is working appropriately. | Users can view that the data view Logic for DRR (Daily Run Rate) is "Target / Month Days" and is working appropriately.
BIR12 | FR-1, KPI: GA | Verify that the data view Logic for CRR (Current Run Rate) is "Achievement/days elapsed" and is working appropriately. | Users can view that the data view Logic for CRR (Current Run Rate) is "Achievement/days elapsed" and is working appropriately.
BIR13 | FR-1, KPI: GA | Verify that the data view Logic for RRR (Required Run Rate) is "(Target - Achievement)/Remaining days" and is working appropriately. | Users can view that the data view Logic for RRR (Required Run Rate) is "(Target - Achievement)/Remaining days" and is working appropriately.
BIR14 | FR-1, KPI: GA | Verify that users can view and browse the “Overall” data table view format with fields (Target(Cumulative Target of Month), MTD Achievement(Cumulative Achievement of MTD), Achievement % (Achievement/ Target)*100, LMTD(Cumulative Achievement of LMTD), MTD Vs LMTD(((MTD-LMTD)/LMTD)*100), DRR(Target / Month Days), CRR(Achievement/Days elapsed), RRR((Target - Achievement)/remaining days), Today(Cumulative Achievement of todays’ till time), Yesterday(Cumulative Achievement of yesterday (Full day)), Last week same day(Cumulative Achievement of last week same day (Full day)). | Users can view and browse the “Overall” data table view format with fields (Target(Cumulative Target of Month), MTD Achievement(Cumulative Achievement of MTD), Achievement % (Achievement/ Target)*100, LMTD(Cumulative Achievement of LMTD), MTD Vs LMTD(((MTD-LMTD)/LMTD)*100), DRR(Target / Month Days), CRR(Achievement/Days elapsed), RRR((Target - Achievement)/remaining days), Today(Cumulative Achievement of todays’ till time), Yesterday(Cumulative Achievement of yesterday (Full day)), Last week same day(Cumulative Achievement of last week same day (Full day)).
BIR15 | FR-1, KPI: GA | Verify that users can view and browse the “BP Wise” data table view format with fields (Target(Cumulative Target of Month), MTD Achievement(Cumulative Achievement of MTD), Achievement % (Achievement/ Target)*100, GA Count Today’s(GA Activation Quantity of Today’s till time), Retail Count MTD(Retail Count of MTD (unique retail with GA)), Retail Count of Today(unique retail with GA)). | Users can view and browse the “BP Wise” data table view format with fields (Target(Cumulative Target of Month), MTD Achievement(Cumulative Achievement of MTD), Achievement % (Achievement/ Target)*100, GA Count Today’s(GA Activation Quantity of Today’s till time), Retail Count MTD(Retail Count of MTD (unique retail with GA)), Retail Count of Today(unique retail with GA)).
BIR16 | FR-1, KPI: GA | Verify that all the Negative growth items/values color are Red. | Users can view that all the Negative growth items/values color are Red.
BIR17 | FR-1, KPI: GA | Verify that all the behind MTD growth items, if MTD Achievement is less than that time's/day's target then the data are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red). | Users can view all the behind MTD growth items, if MTD Achievement is less than that time's/day's targets then the data are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red).
BIR18 | FR-1, KPI: GA | Verify that the Geography Filter feature can be hidden/shown with the filter button. | Users can see that the Geography Filter feature can be hidden/shown with the filter button.
BIR19 | FR-1, KPI: GA | Verify that the MTD Vs LMTD decimal value must be Rounded up to the next integer value. | Users can view that the MTD Vs LMTD decimal value must be Rounded up to the next integer value.
BIR20 | FR-1, KPI: GA | Verify that the DRR, CRR, and RRR decimal values must be Rounded up to the next integer value. | Users can view that the DRR, CRR, and RRR decimal values must be Rounded up to the next integer value.
BIR21 | FR-1, KPI: GA | Verify that the summarized data view must work as the user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her. | Users can view that the summarized data view must work as the user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her.
BIR22 | FR-1, KPI: GA | Verify that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately. | Users can view that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately.
BIR23 | FR-2, KPI: All Bundle | Verify that a new Report feature and page of KPI “All Bundle” is available and browsable appropriately. | Users can view that a new Report feature and page of KPI “All Bundle” is available and browsable appropriately.
BIR24 | FR-2, KPI: All Bundle | Verify that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately. | Users can view that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately.
BIR25 | FR-2, KPI: All Bundle | Verify that User wise summarized data view after login is available and working appropriately. | Users can view that User level wise summarized data view after login is available and working appropriately.
BIR26 | FR-2, KPI: All Bundle | Verify that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page. | Users can view that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page.
BIR27 | FR-2, KPI: All Bundle | Verify that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”. | Users can view that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”.
BIR28 | FR-2, KPI: All Bundle | Verify that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show. | Users can view that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show.
BIR29 | FR-2, KPI: All Bundle | Verify that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”. | Users can view that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”.
BIR30 | FR-2, KPI: All Bundle | Verify that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”. | Users can view that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”.
BIR31 | FR-2, KPI: All Bundle | Verify that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”. | Users can view that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”.
BIR32 | FR-2, KPI: All Bundle | Verify that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”. | Users can view that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”.
BIR33 | FR-2, KPI: All Bundle | Verify that the data view Logic for DRR (Daily Run Rate) is "Target / Month Days" and is working appropriately. | Users can view that the data view Logic for DRR (Daily Run Rate) is "Target / Month Days" and is working appropriately.
BIR34 | FR-2, KPI: All Bundle | Verify that the data view Logic for CRR (Current Run Rate) is "Achievement/days elapsed" and is working appropriately. | Users can view that the data view Logic for CRR (Current Run Rate) is "Achievement/days elapsed" and is working appropriately.
BIR35 | FR-2, KPI: All Bundle | Verify that the data view Logic for RRR (Required Run Rate) is "(Target - Achievement)/Remaining days" and is working appropriately. | Users can view that the data view Logic for RRR (Required Run Rate) is "(Target - Achievement)/Remaining days" and is working appropriately.
BIR36 | FR-2, KPI: All Bundle | Verify that users can view and browse the “All Bundle” data table view format with fields (Target(Cumulative Target of Month), MTD Achievement(Cumulative Achievement of MTD), Achievement % (Achievement/ Target)*100, LMTD(Cumulative Achievement of LMTD, DRR(Target / Month Days), CRR(Achievement/days elapsed), RRR((Target - Achievement)/remaining days), Today(Cumulative Achievement of todays’ till time), Yesterday(Cumulative Achievement of yesterday (Full day)), Last week same day(Cumulative Achievement of last week same day (Full day)). | Users can view and browse the “All Bundle” data table view format with fields (Target(Cumulative Target of Month), MTD Achievement(Cumulative Achievement of MTD), Achievement % (Achievement/ Target)*100, LMTD(Cumulative Achievement of LMTD, DRR(Target / Month Days), CRR(Achievement/Days Elapsed), RRR((Target - Achievement)/remaining days), Today(Cumulative Achievement of todays’ till time), Yesterday(Cumulative Achievement of yesterday (Full day)), Last week same day(Cumulative Achievement of last week same day (Full day)).
BIR37 | FR-2, KPI: All Bundle | Verify that all the Negative growth items/values color are Red. | Users can view that all the Negative growth items/values color are Red.
BIR38 | FR-2, KPI: All Bundle | Verify that all the behind MTD growth items, if MTD Achievement is less than that time/day target’s then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red). | Users can view that all the behind MTD growth items, if MTD Achievement is less than that time/day target’s then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red).
BIR39 | FR-2, KPI: All Bundle | Verify that the Geography Filter feature can be hide/show with the filter button. | Users can view that the Geography Filter feature can be hidden/shown with the filter button.
BIR40 | FR-2, KPI: All Bundle | Verify that the MTD vs LMTD decimal value must be 2 digits. | Users can that the MTD vs LMTD decimal value must be 2 digits.
BIR41 | FR-2, KPI: All Bundle | Verify that the DRR, CRR, and RRR decimal value must be 2 digits. | Users can view that the DRR, CRR, and RRR decimal values must be 2 digits.
BIR42 | FR-2, KPI: All Bundle | Verfiy that the summarized data view must work as user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her. | Users can view that the summarized data view must work as the user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her.
BIR43 | FR-2, KPI: All Bundle | Verify that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately. | Users can view that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately.
BIR44 | FR-3, KPI: Data | Verify that a new Report feature and page of KPI “Data” is available and browsable appropriately. | Users can view that a new Report feature and page of KPI “Data” is available and browsable appropriately.
BIR45 | FR-3, KPI: Data | Verify that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately. | Users can view that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately.
BIR46 | FR-3, KPI: Data | Verify that User wise summarized data view after login is available and working appropriately. | Users can view that User level wise summarized data view after login is available and working appropriately.
BIR47 | FR-3, KPI: Data | Verify that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page. | Users can view that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page.
BIR48 | FR-3, KPI: Data | Verify that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”. | Users can view that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”.
BIR49 | FR-3, KPI: Data | Verify that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show. | Users can view that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show.
BIR50 | FR-3, KPI: Data | Verify that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”. | Users can view that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”.
BIR51 | FR-3, KPI: Data | Verify that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”. | Users can view that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”.
BIR52 | FR-3, KPI: Data | Verify that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”. | Users can view that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”.
BIR53 | FR-3, KPI: Data | Verify that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”. | Users can view that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”.
BIR54 | FR-3, KPI: Data | Verify that the data view Logic for DRR (Daily Run Rate) is "Target / Month Days" and is working appropriately. | Users can view that the data view Logic for DRR (Daily Run Rate) is "Target / Month Days" and is working appropriately.
BIR55 | FR-3, KPI: Data | Verify that the data view Logic for CRR (Current Run Rate) is "Achievement/days elapsed" and is working appropriately. | Users can view that the data view Logic for CRR (Current Run Rate) is "Achievement/days elapsed" and is working appropriately.
BIR56 | FR-3, KPI: Data | Verify that the data view Logic for RRR (Required Run Rate) is "(Target - Achievement)/Remaining days" and is working appropriately. | Users can view that the data view Logic for RRR (Required Run Rate) is "(Target - Achievement)/Remaining days" and is working appropriately.
BIR57 | FR-3, KPI: Data | Verify that users can view and browse the the “Data” table view format with fields (Target(Cumulative Target of Month), MTD Achievement(Cumulative Achievement of MTD), Achievement % (Achievement/ Target)*100, LMTD(Cumulative Achievement of LMTD), MTD Vs LMTD(((MTD-LMTD)/LMTD)*100), CRR(Achievement / days elapsed), RRR((Target - Achievement)/remaining days), Today(Cumulative Achievement of todays’ till time), Yesterday(Cumulative Achievement of yesterday (Full day)), Last week same day(Cumulative Achievement of last week same day (Full day)). | Users can view and browse the “Data” table view format with fields (Target(Cumulative Target of Month), MTD Achievement(Cumulative Achievement of MTD), Achievement % (Achievement/ Target)*100, LMTD(Cumulative Achievement of LMTD), MTD Vs LMTD(((MTD-LMTD)/LMTD)*100), CRR(Achievement/days elapsed), RRR((Target - Achievement)/remaining days), Today(Cumulative Achievement of todays’ till time), Yesterday(Cumulative Achievement of yesterday (Full day)), Last week same day(Cumulative Achievement of last week same day (Full day)).
BIR58 | FR-3, KPI: Data | Verify that all the Negative growth items/values color are Red. | Users can view that all the Negative growth items/values color are Red.
BIR59 | FR-3, KPI: Data | Verify that all the behind MTD growth items, if MTD Achievement is less than that time/day target’s then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red). | Users can view that all the behind MTD growth items, if MTD Achievement is less than that time/day target’s then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red).
BIR60 | FR-3, KPI: Data | Verify that the Geography Filter feature can be hide/show with the filter button. | Users can view that the Geography Filter feature can be hidden/shown with the filter button.
BIR61 | FR-3, KPI: Data | Verify that the MTD vs LMTD decimal value must be 2 digits. | Users can that the MTD vs LMTD decimal value must be 2 digits.
BIR62 | FR-3, KPI: Data | Verify that for the DRR, CRR, RR decimal value must 2 digits. | Users can view that the DRR, CRR, and RRR decimal values must 2 digits.
BIR63 | FR-3, KPI: Data | Verfiy that the summarized data view must work as user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her. | Users can view that the summarized data view must work as user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her.
BIR64 | FR-3, KPI: Data | Verify that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately. | Users can view that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately.
BIR65 | FR-4, KPI: EV | Verify that a new Report feature and page of KPI “EV” is available and browsable appropriately. | Users can view that a new Report feature and page of KPI “EV” is available and browsable appropriately.
BIR66 | FR-4, KPI: EV | Verify that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately. | Users can view that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately.
BIR67 | FR-4, KPI: EV | Verify that User wise summarized data view after login is available and working appropriately. | Users can view that User level wise summarized data view after login is available and working appropriately.
BIR68 | FR-4, KPI: EV | Verify that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page. | Users can view that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page.
BIR69 | FR-4, KPI: EV | Verify that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”. | Users can view that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”.
BIR70 | FR-4, KPI: EV | Verify that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show. | Users can view that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show.
BIR71 | FR-4, KPI: EV | Verify that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”. | Users can view that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”.
BIR72 | FR-4, KPI: EV | Verify that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”. | Users can view that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”.
BIR73 | FR-4, KPI: EV | Verify that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”. | Users can view that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”.
BIR74 | FR-4, KPI: EV | Verify that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”. | Users can view that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”.
BIR75 | FR-4, KPI: EV | Verify that users can view and browse the “EV Tertiary” table view format with fields (MTD Achievement (Cumulative Achievement of MTD), LMTD (Cumulative Achievement of LMTD), Today (Cumulative Achievement of todays’ till time), Yesterday (Cumulative Achievement of yesterday (Full day)), Last week same day (Cumulative Achievement of last week same day (Full day)). | Users can view and browse the “EV Tertiary” table view format with fields (MTD Achievement (Cumulative Achievement of MTD), LMTD (Cumulative Achievement of LMTD), Today (Cumulative Achievement of today’s till time), Yesterday (Cumulative Achievement of yesterday (Full day)), Last week same day (Cumulative Achievement of last week same day (Full day)).
BIR76 | FR-4, KPI: EV | Verify that users can view and browse the “EV Secondary” table view format with fields (Target (Cumulative Target of Month), MTD Achievement (Cumulative Achievement of MTD), Achievement % (Achievement/ Target) *100, LMTD (Cumulative Achievement of LMTD), MTD Vs LMTD(((MTD-LMTD)/LMTD) *100), DTR (O2C data), GAP with Tertiary (Gap between (C2C / C2S – C2C)/100)). | Users can view and browse the “EV Secondary” table view format with fields (Target (Cumulative Target of Month), MTD Achievement (Cumulative Achievement of MTD), Achievement % (Achievement/ Target) *100, LMTD (Cumulative Achievement of LMTD), MTD Vs LMTD(((MTD-LMTD)/LMTD) *100), DTR (O2C data), GAP with Tertiary (Gap between (C2C / C2S – C2C)/100)).
BIR77 | FR-4, KPI: EV | Verify that all the Negative growth items/values color are Red. | Users can view that all the Negative growth items/values color are Red.
BIR78 | FR-4, KPI: EV | Verify that all the behind MTD growth items, if MTD Achievement is less than that time/day target’s then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red). | Users can view all the behind MTD growth items, if MTD Achievement is less than that time/day target then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red).
BIR79 | FR-4, KPI: EV | Verify that the Geography Filter feature can be hide/show with the filter button. | Users can view that the Geography Filter feature can be hiden/show with the filter button.
BIR80 | FR-4, KPI: EV | Verify that the MTD vs LMTD decimal value should display 2 decimal value. | Users can view that the MTD vs LMTD decimal value should display 2 decimal values.
BIR81 | FR-4, KPI: EV | Verify that the Gap with Tertiary should display 2 decimal value. | Users can view that the Gap with Tertiary should display 2 decimal values.
BIR82 | FR-4, KPI: EV | Verfiy that the summarized data view must work as user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her. | Users can view that the summarized data view must work as the user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her.
BIR83 | FR-4, KPI: EV | Verify that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately. | Users can view that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately.
BIR84 | FR-5, KPI: SC | Verify that a new Report feature and page of KPI “SC” is available and browsable appropriately. | Users can view that a new Report feature and page of KPI “SC” is available and browsable appropriately.
BIR85 | FR-5, KPI: SC | Verify that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately. | Users can view that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately.
BIR86 | FR-5, KPI: SC | Verify that User wise summarized data view after login is available and working appropriately. | Users can view that User level wise summarized data view after login is available and working appropriately.
BIR87 | FR-5, KPI: SC | Verify that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page. | Users can view that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page.
BIR88 | FR-5, KPI: SC | Verify that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”. | Users can view that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”.
BIR89 | FR-5, KPI: SC | Verify that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show. | Users can view that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show.
BIR90 | FR-5, KPI: SC | Verify that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”. | Users can view that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”.
BIR91 | FR-5, KPI: SC | Verify that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”. | Users can view that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”.
BIR92 | FR-5, KPI: SC | Verify that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”. | Users can view that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”.
BIR93 | FR-5, KPI: SC | Verify that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”. | Users can view that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”.
BIR94 | FR-5, KPI: SC | Verify that users can view and browse the “SC Primary” table view format with fields (Target (Cumulative Target of Month), MTD Achievement (Cumulative Achievement of MTD), Achievement % (Achievement/ Target) *100, LMTD (Cumulative Achievement of LMTD). | Users can view and browse the “SC Primary” table view format with fields (Target (Cumulative Target of Month), MTD Achievement (Cumulative Achievement of MTD), Achievement % (Achievement/ Target) *100, LMTD (Cumulative Achievement of LMTD).
BIR95 | FR-5, KPI: SC | Verify that users can view and browse the “SC Secondary” table view format with fields (Target (Cumulative Target of Month), MTD Achievement (Cumulative Achievement of MTD), Achievement % (Achievement/ Target) *100, LMTD (Cumulative Achievement of LMTD). | Users can view and browse the “SC Secondary” table view format with fields (Target (Cumulative Target of Month), MTD Achievement (Cumulative Achievement of MTD), Achievement % (Achievement/ Target) *100, LMTD (Cumulative Achievement of LMTD).
BIR96 | FR-5, KPI: SC | Verify that users can view and browse the “SC Tertiary” table view format with fields (Target (Cumulative Target of Month), MTD Achievement (Cumulative Achievement of MTD), Achievement % (Achievement/ Target) *100, LMTD (Cumulative Achievement of LMTD). | Users can view and browse the “SC Tertiary” table view format with fields (Target (Cumulative Target of Month), MTD Achievement (Cumulative Achievement of MTD), Achievement % (Achievement/ Target) *100, LMTD (Cumulative Achievement of LMTD).
BIR97 | FR-5, KPI: SC | Verify that all the Negative growth items/values color are Red. | Users can view that all the Negative growth items/values color are Red.
BIR98 | FR-5, KPI: SC | Verify that all the behind MTD growth items, if MTD Achievement is less than that time/day target’s then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red). | Users can view all the behind MTD growth items, if MTD Achievement is less than that time/day target then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red).
BIR99 | FR-5, KPI: SC | Verify that the Geography Filter feature can be hide/show with the filter button. | Users can view that the Geography Filter feature can be hiden/shown with the filter button.
BIR100 | FR-5, KPI: SC | Verify that the MTD vs LMTD decimal value is Rounded up to the next integer value. | Users can view that the MTD vs LMTD decimal value is Rounded up to the next integer value.
BIR101 | FR-5, KPI: SC | Verfiy that the summarized data view must work as user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her. | Users can view that the summarized data view must work as the user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her.
BIR102 | FR-5, KPI: SC | Verify that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately. | Users can view that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately.
BIR103 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that a new Report feature and page of KPI “LSO, DLSO, SSO, DSSO, BSO, DSO” is available and browsable appropriately. | Users can view that a new Report feature and page of KPI “LSO, DLSO, SSO, DSSO, BSO, DSO” is available and browsable appropriately.
BIR104 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately. | Users can view that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately.
BIR105 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that User wise summarized data view after login is available and working appropriately. | Users can view that User level wise summarized data view after login is available and working appropriately.
BIR106 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page. | Users can view that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page.
BIR107 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”. | Users can view that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”.
BIR108 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show. | Users can view that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show.
BIR109 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”. | Users can view that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”.
BIR110 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”. | Users can view that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”.
BIR111 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”. | Users can view that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”.
BIR112 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”. | Users can view that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”.
BIR113 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that users can view and browse the “LSO, DLSO, SSO, DSSO, BSO, DSO” table view format with fields (Target (Cumulative Target of Month), MTD (Total Amount and Percentage (%), MTD (%) (Total Amount and Percentage (%)*100), LMTD (Cumulative Achievement of LMTD)). | Users can view and browse the “LSO, DLSO, SSO, DSSO, BSO, DSO” table view format with fields (Target (Cumulative Target of Month), MTD (Total Amount and Percentage (%), MTD (%) (Total Amount and Percentage (%)*100), LMTD (Cumulative Achievement of LMTD)).
BIR114 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that users can view and use the dropdown feature with options (LSO, DLSO, SSO, DSSO, BSO, DSO). | Users can view and use the dropdown feature with options (LSO, DLSO, SSO, DSSO, BSO, DSO).
BIR115 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that users can view and browse all the (LSO, DLSO, SSO, DSSO, BSO, DSO) data view on the default landing page. | Users can view and browse all the (LSO, DLSO, SSO, DSSO, BSO, DSO) data view on the default landing page.
BIR116 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that all the Negative growth items/values color are Red. | Users can view that all the Negative growth items/values color are Red.
BIR117 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that all the behind MTD growth items, if MTD Achievement is less than that time/day target’s then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red). | Users can view all the behind MTD growth items, if MTD Achievement is less than that time/day target then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red).
BIR118 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that the Geography Filter feature can be hide/show with the filter button. | Users can view that the Geography Filter feature can be hidden/shown with the filter button.
BIR119 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that the MTD vs LMTD decimal value is Rounded up to the next integer value. | Users view that the MTD vs LMTD decimal value is Rounded up to the the next integer value.
BIR120 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verfiy that the summarized data view must work as user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her. | Users can view that the summarized data view must work as the user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her.
BIR121 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that users can view and select the values in the Geography filter under his/her low level of Geography. Example: ZM can view and select the values in the “Distributor”, “RSO Supervisor”, and “RSO” dropdowns under the ZM. | Users can view and select the values in the Geography filter under his/her low level of Geography. Example: ZM can view and select the values in the “Distributor”, “RSO Supervisor”, and “RSO” dropdowns under the ZM.
BIR122 | FR-6, KPI: LSO, DLSO, SSO, DSSO, BSO, DSO | Verify that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately. | Users can view that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately.
BIR123 | FR-7, KPI: M1/M2 Decay | Verify that a new Report feature and page of KPI “M1/M2 Decay” is available and browsable appropriately. | Users can view that a new Report feature and page of KPI “M1/M2 Decay” is available and browsable appropriately.
BIR124 | FR-7, KPI: M1/M2 Decay | Verify that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately. | Users can view that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately.
BIR125 | FR-7, KPI: M1/M2 Decay | Verify that User wise summarized data view after login is available and working appropriately. | Users can view that User level wise summarized data view after login is available and working appropriately.
BIR126 | FR-7, KPI: M1/M2 Decay | Verify that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page. | Users can view that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page.
BIR127 | FR-7, KPI: M1/M2 Decay | Verify that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”. | Users can view that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”.
BIR128 | FR-7, KPI: M1/M2 Decay | Verify that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show. | Users can view that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show.
BIR129 | FR-7, KPI: M1/M2 Decay | Verify that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”. | Users can view that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”.
BIR130 | FR-7, KPI: M1/M2 Decay | Verify that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”. | Users can view that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”.
BIR131 | FR-7, KPI: M1/M2 Decay | Verify that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”. | Users can view that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”.
BIR132 | FR-7, KPI: M1/M2 Decay | Verify that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”. | Users can view that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”.
BIR133 | FR-7, KPI: M1/M2 Decay | Verify that users can view and browse the “M1 Decay” table view format with fields (Retail GA (Decay), BP GA (Decay) and Total (Decay)= ((Decay M1 /Total GA of M1) *100)). | Users can view and browse the “M1 Decay” table view format with fields (Retail GA (Decay), BP GA (Decay) and Total (Decay)= ((Decay M1 /Total GA of M1) *100)).
BIR134 | FR-7, KPI: M1/M2 Decay | Verify that users can view and browse the “M2 Decay” table view format with fields ((Retail GA (Decay), BP GA (Decay) and Total (Decay)= ((Decay M2 /Total GA of M2) *100)). | Users can view and browse the “M2 Decay” table view format with fields ((Retail GA (Decay), BP GA (Decay) and Total (Decay)= ((Decay M2 /Total GA of M2) *100)).
BIR135 | FR-7, KPI: M1/M2 Decay | Verify that all the Negative growth items/values color are Red. | Users can view that all the Negative growth items/values color are Red.
BIR136 | FR-7, KPI: M1/M2 Decay | Verify that all the behind MTD growth items, if MTD Achievement is less than that time/day target’s then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red). | Users can view all the behind MTD growth items, if MTD Achievement is less than that time/day target then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red).
BIR137 | FR-7, KPI: M1/M2 Decay | Verify that the Geography Filter feature can be hide/show with the filter button. | Users can view that the Geography Filter feature can be hidden/shown with the filter button.
BIR138 | FR-7, KPI: M1/M2 Decay | Verify that the MTD vs LMTD decimal value should be Rounded up to next integer value. | Users view that the MTD vs LMTD decimal value be Rounded up to the next integer value.
BIR139 | FR-7, KPI: M1/M2 Decay | Verfiy that the summarized data view must work as user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her. | Users can view that the summarized data view must work as the user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her.
BIR140 | FR-7, KPI: M1/M2 Decay | Verify that users can view and select the values in Geography filter under his/her low level of the Geography. Example: ZM can view and select the values in “Distributor”, “RSO Supervisor”, and “RSO” dropdown under the ZM. | Users can view and select the values in the Geography filter under his/her low level of Geography. Example: ZM can view and select the values in the “Distributor”, “RSO Supervisor”, and “RSO” dropdowns under the ZM.
BIR141 | FR-7, KPI: M1/M2 Decay | Verify that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately. | Users can view that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately.
BIR142 | FR-8, KPI: App Utilization | Verify that a new Report feature and page of KPI “App Utilization” is available and browsable appropriately. | Users can view that a new Report feature and page of KPI “App Utilization” is available and browsable appropriately.
BIR143 | FR-8, KPI: App Utilization | Verify that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately. | Users can view that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately.
BIR144 | FR-8, KPI: App Utilization | Verify that User wise summarized data view after login is available and working appropriately. | Users can view that User level wise summarized data view after login is available and working appropriately.
BIR145 | FR-8, KPI: App Utilization | Verify that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page. | Users can view that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page.
BIR146 | FR-8, KPI: App Utilization | Verify that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”. | Users can view that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”.
BIR147 | FR-8, KPI: App Utilization | Verify that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show. | Users can view that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show.
BIR148 | FR-8, KPI: App Utilization | Verify that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”. | Users can view that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”.
BIR149 | FR-8, KPI: App Utilization | Verify that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”. | Users can view that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”.
BIR150 | FR-8, KPI: App Utilization | Verify that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”. | Users can view that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”.
BIR151 | FR-8, KPI: App Utilization | Verify that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”. | Users can view that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”.
BIR152 | FR-8, KPI: App Utilization | Verify that users can view and browse the “Retailer App Utilization” table view format with fields (LSO Count (Cumulative count of Load Selling Outlet), Retailer App User (Cumulative count of App user), App User (%) ((App user / Total Retailer) * 100), Overall C2S (Cumulative Count of C2S), Retailer App C2S (Cumulative count of C2S from Retailer App), Utilization (%) ((App C2S count / Overall Count) * 100)). | Users can view and browse the “Retailer App Utilization” table view format with fields (LSO Count (Cumulative count of Load Selling Outlet), Retailer App User (Cumulative count of App user), App User (%) ((App user / Total Retailer) * 100), Overall C2S (Cumulative Count of C2S), Retailer App C2S (Cumulative count of C2S from Retailer App), Utilization (%) ((App C2S count / Overall Count) * 100)).
BIR153 | FR-8, KPI: App Utilization | Verify that users can view and browse the “RSO App Utilization” table view format with fields (RSO Count (Cumulative count of RSO Count), RSO App user (Cumulative count of App user), App user (%) ((App user / Total RSO) * 100), Overall C2C Count (Cumulative count of C2C), RSO App C2C Count (Cumulative count of C2C from RSO App), Utilization (%) ((App C2S Amount / Overall C2S Amount) * 100)). | Users can view and browse the “RSO App Utilization” table view format with fields (RSO Count (Cumulative count of RSO Count), RSO App user (Cumulative count of App user), App user (%) ((App user / Total RSO) * 100), Overall C2C Count (Cumulative count of C2C), RSO App C2C Count (Cumulative count of C2C from RSO App), Utilization (%) ((App C2S Amount / Overall C2S Amount) * 100)).
BIR154 | FR-8, KPI: App Utilization | Verify that users can view and browse the “RSO App Utilization” Plan, Visited, Memo table view format with fields (Plan Visit (Retail Count of D-1), Actual visit (Visited Retail Count of D-1), Actual Visit (%) ((Actual Visit count/ Plan Visit count) * 100), Memo (Memo Count of D-1), Memo (%) ((MEMO count/ Actual Visit count) * 100)). | Users can view and browse the “RSO App Utilization” Plan, Visited, Memo table view format with fields (Plan Visit (Retail Count of D-1), Actual visit (Visited Retail Count of D-1), Actual Visit (%) ((Actual Visit count/ Plan Visit count) * 100), Memo (Memo Count of D-1), Memo (%) ((MEMO count/ Actual Visit count) * 100)).
BIR155 | FR-8, KPI: App Utilization | Verify that all the Negative growth items/values color are Red. | Users can view that all the Negative growth items/values color are Red.
BIR156 | FR-8, KPI: App Utilization | Verify that all the behind MTD growth items, if MTD Achievement is less than that time/day target’s then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red). | Users can view all the behind MTD growth items, if MTD Achievement is less than that time/day target then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red).
BIR157 | FR-8, KPI: App Utilization | Verify that the Geography Filter feature can be hide/show with the filter button. | Users can view that the Geography Filter feature can be hidden/shown with the filter button.
BIR158 | FR-8, KPI: App Utilization | Verify that for all the decimal value is Rounded up to the next integer value. | Users view that the MTD vs LMTD decimal value be Rounded up to the next integer value.
BIR159 | FR-8, KPI: App Utilization | Verfiy that the summarized data view must work as user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her. | Users can view that the summarized data view must work as the user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her.
BIR160 | FR-8, KPI: App Utilization | Verify that users can view and select the values in Geography filter under his/her low level of the Geography. Example: ZM can view and select the values in “Distributor”, “RSO Supervisor”, and “RSO” dropdown under the ZM. | Users can view and select the values in the Geography filter under his/her low level of Geography. Example: ZM can view and select the values in the “Distributor”, “RSO Supervisor”, and “RSO” dropdowns under the ZM.
BIR161 | FR-8, KPI: App Utilization | Verify that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately. | Users can view that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately.
BIR162 | FR-9, KPI: Deno | Verify that a new Report feature and page of KPI “Deno” is available and browsable appropriately. | Users can view that a new Report feature and page of KPI “Deno” is available and browsable appropriately.
BIR163 | FR-9, KPI: Deno | Verify that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately. | Users can view that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately.
BIR164 | FR-9, KPI: Deno | Verify that User wise summarized data view after login is available and working appropriately. | Users can view that User level wise summarized data view after login is available and working appropriately.
BIR165 | FR-9, KPI: Deno | Verify that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page. | Users can view that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page.
BIR166 | FR-9, KPI: Deno | Verify that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”. | Users can view that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”.
BIR167 | FR-9, KPI: Deno | Verify that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show. | Users can view that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show.
BIR168 | FR-9, KPI: Deno | Verify that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”. | Users can view that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”.
BIR169 | FR-9, KPI: Deno | Verify that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”. | Users can view that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”.
BIR170 | FR-9, KPI: Deno | Verify that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”. | Users can view that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”.
BIR171 | FR-9, KPI: Deno | Verify that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”. | Users can view that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”.
BIR172 | FR-9, KPI: Deno | Verify that users can view and browse the “Deno” table view format with fields (Today (Cumulative Achievement of todays’ till time), Retail Count (Cumulative count of Load Selling outlet), Transaction Count (Cumulative count of Load Selling outlet), Yesterday (Cumulative Achievement of yesterday (Full day)), Last week same day (Cumulative Achievement of last week same day (Full day)), MTD (Total Amount and Percentage (%)), LMTD (Cumulative Achievement of LMTD)). | Users can view and browse the “Deno” table view format with fields (Today (Cumulative Achievement of today’s till time), Retail Count (Cumulative count of Load Selling outlet), Transaction Count (Cumulative count of Load Selling outlet), Yesterday (Cumulative Achievement of yesterday (Full day)), Last week same day (Cumulative Achievement of last week same day (Full day)), MTD (Total Amount and Percentage (%)), LMTD (Cumulative Achievement of LMTD)).
BIR173 | FR-9, KPI: Deno | Verify that all the Negative growth items/values color are Red. | Users can view that all the Negative growth items/values color are Red.
BIR174 | FR-9, KPI: Deno | Verify that all the behind MTD growth items, if MTD Achievement is less than that time/day target’s then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red). | Users can view all the behind MTD growth items, if MTD Achievement is less than that time/day target then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red).
BIR175 | FR-9, KPI: Deno | Verify that the Geography Filter feature can be hide/show with the filter button. | Users can view that the Geography Filter feature can be hidden/shown with the filter button.
BIR176 | FR-9, KPI: Deno | Verify that for the "MTD vs LMTD" the decimal value is 2 digit. | Users view that the MTD vs LMTD decimal value be Rounded up to the next integer value.
BIR177 | FR-9, KPI: Deno | Verfiy that the summarized data view must work as user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her. | Users can view that the summarized data view must work as the user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her.
BIR178 | FR-9, KPI: Deno | Verify that users can view and select the values in Geography filter under his/her low level of the Geography. Example: ZM can view and select the values in “Distributor”, “RSO Supervisor”, and “RSO” dropdown under the ZM. | Users can view and select the values in the Geography filter under his/her low level of Geography. Example: ZM can view and select the values in the “Distributor”, “RSO Supervisor”, and “RSO” dropdowns under the ZM.
BIR179 | FR-9, KPI: Deno | Verify that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately. | Users can view that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately.
BIR180 | FR-10, KPI: Deno Sub-base | Verify that a new Report feature and page of KPI “Deno Sub-base” is available and browsable appropriately. | Users can view that a new Report feature and page of KPI “Deno Sub-base” is available and browsable appropriately.
BIR181 | FR-10, KPI: Deno Sub-base | Verify that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately. | Users can view that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately.
BIR182 | FR-10, KPI: Deno Sub-base | Verify that User wise summarized data view after login is available and working appropriately. | Users can view that User level wise summarized data view after login is available and working appropriately.
BIR183 | FR-10, KPI: Deno Sub-base | Verify that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page. | Users can view that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page.
BIR184 | FR-10, KPI: Deno Sub-base | Verify that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”. | Users can view that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”.
BIR185 | FR-10, KPI: Deno Sub-base | Verify that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show. | Users can view that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show.
BIR186 | FR-10, KPI: Deno Sub-base | Verify that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”. | Users can view that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”.
BIR187 | FR-10, KPI: Deno Sub-base | Verify that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”. | Users can view that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”.
BIR188 | FR-10, KPI: Deno Sub-base | Verify that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”. | Users can view that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”.
BIR189 | FR-10, KPI: Deno Sub-base | Verify that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”. | Users can view that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”.
BIR190 | FR-10, KPI: Deno Sub-base | Verify that users can view and browse the “Deno Sub-base” table view format with fields (Subbase, Today (Cumulative Achievement of today’s till time), Yesterday (Cumulative Achievement of yesterday (Full day)), Last week same day (Cumulative Achievement of last week same day (Full day)), MTD (Total Amount and Percentage (%)), LMTD (Cumulative Achievement of LMTD)) with dropdown selection feature “Deno Amount (Hero Deno from DMS)”, and 3D, 7D, 30D Tab selection feature. | Users can view and browse the “Deno Sub-base” table view format with fields (Subbase, Today (Cumulative Achievement of today’s till time), Yesterday (Cumulative Achievement of yesterday (Full day)), Last week same day (Cumulative Achievement of last week same day (Full day)), MTD (Total Amount and Percentage (%)), LMTD (Cumulative Achievement of LMTD)) with dropdown selection feature “Deno Amount (Hero Deno from DMS)”, and 3D, 7D, 30D Tab selection feature.
BIR191 | FR-10, KPI: Deno Sub-base | Verify that all the Negative growth items/values color are Red. | Users can view that all the Negative growth items/values color are Red.
BIR192 | FR-10, KPI: Deno Sub-base | Verify that all the behind MTD growth items, if MTD Achievement is less than that time/day target’s then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red). | Users can view all the behind MTD growth items, if MTD Achievement is less than that time/day target then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red).
BIR193 | FR-10, KPI: Deno Sub-base | Verify that the Geography Filter feature can be hide/show with the filter button. | Users can view that the Geography Filter feature can be hidden/shown with the filter button.
BIR194 | FR-10, KPI: Deno Sub-base | Verify that for the "MTD vs LMTD" the decimal value should be Rounded up to next integer value. | Users view that the MTD vs LMTD decimal value be Rounded up to the next integer value.
BIR195 | FR-10, KPI: Deno Sub-base | Verfiy that the summarized data view must work as user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her. | Users can view that the summarized data view must work as the user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her.
BIR196 | FR-10, KPI: Deno Sub-base | Verify that users can view and select the values in Geography filter under his/her low level of the Geography. Example: ZM can view and select the values in “Distributor”, “RSO Supervisor”, and “RSO” dropdown under the ZM. | Users can view and select the values in the Geography filter under his/her low level of Geography. Example: ZM can view and select the values in the “Distributor”, “RSO Supervisor”, and “RSO” dropdowns under the ZM.
BIR197 | FR-10, KPI: Deno Sub-base | Verify that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately. | Users can view that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately.
BIR198 | FR-11, KPI: Site | Verify that a new Report feature and page of KPI “Site” is available and browsable appropriately. | Users can view that a new Report feature and page of KPI “Site” is available and browsable appropriately.
BIR199 | FR-11, KPI: Site | Verify that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately. | Users can view that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately.
BIR200 | FR-11, KPI: Site | Verify that User wise summarized data view after login is available and working appropriately. | Users can view that User level wise summarized data view after login is available and working appropriately.
BIR201 | FR-11, KPI: Site | Verify that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page. | Users can view that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page.
BIR202 | FR-11, KPI: Site | Verify that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”. | Users can view that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”.
BIR203 | FR-11, KPI: Site | Verify that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show. | Users can view that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show.
BIR204 | FR-11, KPI: Site | Verify that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”. | Users can view that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”.
BIR205 | FR-11, KPI: Site | Verify that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”. | Users can view that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”.
BIR206 | FR-11, KPI: Site | Verify that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”. | Users can view that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”.
BIR207 | FR-11, KPI: Site | Verify that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”. | Users can view that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”.
BIR208 | FR-11, KPI: Site | Verify that users can view and browse the “Site” table view format with fields (GA, Subbase, Revenue, Data Revenue, Voice Revenue, LSO MTD, LSO LMTD, SSO MTD, SSO LMTD) | Users can view and browse the “Site” table view format with fields (GA, Subbase, Revenue, Data Revenue, Voice Revenue, LSO MTD, LSO LMTD, SSO MTD, SSO LMTD)
BIR209 | FR-11, KPI: Site | Verify that all the Negative growth items/values color are Red. | Users can view that all the Negative growth items/values color are Red.
BIR210 | FR-11, KPI: Site | Verify that all the behind MTD growth items, if MTD Achievement is less than that time/day target’s then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red). | Users can view all the behind MTD growth items, if MTD Achievement is less than that time/day target then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red).
BIR211 | FR-11, KPI: Site | Verify that the Geography Filter feature can be hide/show with the filter button. | Users can view that the Geography Filter feature can be hidden/shown with the filter button.
BIR212 | FR-11, KPI: Site | Verfiy that the summarized data view must work as user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her. | Users can view that the summarized data view must work as the user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her.
BIR213 | FR-11, KPI: Site | Verify that users can view and select the values in Geography filter under his/her low level of the Geography. Example: ZM can view and select the values in “Distributor”, “RSO Supervisor”, and “RSO” dropdown under the ZM. | Users can view and select the values in the Geography filter under his/her low level of Geography. Example: ZM can view and select the values in the “Distributor”, “RSO Supervisor”, and “RSO” dropdowns under the ZM.
BIR214 | FR-11, KPI: Site | Verify that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately. | Users can view that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately.
BIR215 | FR-12, KPI: Retail SCR | Verify that a new Report feature and page of KPI “Retail SCR” is available and browsable appropriately. | Users can view that a new Report feature and page of KPI “Retail SCR” is available and browsable appropriately.
BIR216 | FR-12, KPI: Retail SCR | Verify that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately. | Users can view that the Geography filter feature with selectable options of (Cluster, Region, Zone, Distributor, RSO Sup, and RSO) is available and working appropriately.
BIR217 | FR-12, KPI: Retail SCR | Verify that User wise summarized data view after login is available and working appropriately. | Users can view that User level wise summarized data view after login is available and working appropriately.
BIR218 | FR-12, KPI: Retail SCR | Verify that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page. | Users can view that to view summarized data for Top (Cluster Director, Director) level users, users must view all “Clusters” summarized data on the default page.
BIR219 | FR-12, KPI: Retail SCR | Verify that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”. | Users can view that after selecting a “Cluster” users must see summarized data of all the “Regions” under that selected “Cluster”.
BIR220 | FR-12, KPI: Retail SCR | Verify that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show. | Users can view that after selecting a “Region” under a “Cluster” users can view and browse summarized data of all the “Zones” under that selected “Region” must show.
BIR221 | FR-12, KPI: Retail SCR | Verify that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”. | Users can view that after selecting a “Zone” under a “Region” users can see summarized data of all the “Distributors” under that selected “Zone”.
BIR222 | FR-12, KPI: Retail SCR | Verify that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”. | Users can view that after selecting a “Distributors” under a “Zone” users can see summarized data of all the “RSO Supervisors” under that selected “Distributor”.
BIR223 | FR-12, KPI: Retail SCR | Verify that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”. | Users can view that after selecting an “RSO Supervisor” under a “Distributor” users can see summarized data of all the “RSOs” under that selected “RSO Supervisor’s”.
BIR224 | FR-12, KPI: Retail SCR | Verify that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”. | Users can view that after selecting an “RSO” under an “RSO Supervisor” users can see summarized data of all the “Retailers” under that selected “RSO”.
BIR225 | FR-12, KPI: Retail SCR | Verify that users can view and browse the “Retail SCR” table view format with fields (Less than 1 Day Stock Retail Count (Retail count of D-1 who has Less than 1-day stock), Less than 1 Day Stock Retail Count Retail (%) ((Less than 1 Day Retail Count/ Total Retail) * 100), Less than 2 Day Stock Retail Count (Retail count of D-1 who has Less than 2-day stock), Less than 2 Day Stock Retail Count Retail (%) ((Less than 2 Day Retail Count/ Total Retail) * 100)). | Users can view and browse the “Retail SCR” table view format with fields (Less than 1 Day Stock Retail Count (Retail count of D-1 who has Less than 1-day stock), Less than 1 Day Stock Retail Count Retail (%) ((Less than 1 Day Retail Count/ Total Retail) * 100), Less than 2 Day Stock Retail Count (Retail count of D-1 who has Less than 2-day stock), Less than 2 Day Stock Retail Count Retail (%) ((Less than 2 Day Retail Count/ Total Retail) * 100)).
BIR226 | FR-12, KPI: Retail SCR | Verify that all the Negative growth items/values color are Red. | Users can view that all the Negative growth items/values color are Red.
BIR227 | FR-12, KPI: Retail SCR | Verify that all the behind MTD growth items, if MTD Achievement is less than that time/day target’s then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red). | Users can view all the behind MTD growth items, if MTD Achievement is less than that time/day target then they are colored if the deviation is equal or less than 5% the color is yellow else the Target vs MTD Achievement deviation is more than 5% the color is Red).
BIR228 | FR-12, KPI: Retail SCR | Verify that the Geography Filter feature can be hide/show with the filter button. | Users can view that the Geography Filter feature can be hidden/shown with the filter button.
BIR229 | FR-12, KPI: Retail SCR | Verfiy that the summarized data view must work as user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her. | Users can view that the summarized data view must work as the user’s hierarchy & demography. Example: RSO will see Retailers summarized data under him/her, RSO Supervisor will see RSOs summarized data under him/her.
BIR230 | FR-12, KPI: Retail SCR | Verify that users can view and select the values in Geography filter under his/her low level of the Geography. Example: ZM can view and select the values in “Distributor”, “RSO Supervisor”, and “RSO” dropdown under the ZM. | Users can view and select the values in the Geography filter under his/her low level of Geography. Example: ZM can view and select the values in the “Distributor”, “RSO Supervisor”, and “RSO” dropdowns under the ZM.
BIR231 | FR-12, KPI: Retail SCR | Verify that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately. | Users can view that all the percentage values are showing 2 decimal values with percentage icon on the UI appropriately.